## Blad1
THIS WEEK | Tasks: | Completed on time: | Estimated: | Actual: | Remarks:
Jasper
Testing |  | yes | 4 | 2 | Tested ExtraLifePowerUp and fixed Ball test.
Fix Violations |  | yes | 4 | 4
Write options menu requirements |  | yes | 2 | 1
Create UML |  | yes | 2 | 1
Implement options menu |  | yes | 5 | 5
Matthias
Testing |  | no | 4 | 0
Fix Violations |  | no | 4 | 0
Exercise 3 |  | yes | 2 | 2
Add power-up icons |  | no | 1 | 0
Arjan
Testing |  | yes | 4 | 4
Fix Violations |  | yes | 4 | 4
Game-over state |  | no | 3 | 3
Bart
Testing |  | no | 4 | 0
Fix Violations |  | no | 4 | 0
Create class diagram (observer pattern) |  | yes | 2 | 2
Create sequence diagram (obeserver pattern) |  | yes | 2 | 2
Luke
Testing |  | No | 4 | 0
Fix Violations |  | Yes | 4 | 2
Write options menu requirements |  | Yes | 2 | 1
Implement singleton pattern |  | Yes | 4 | 3
Create class diagram (2) |  | Yes | 2 | 1
Create sequence diagram (2) |  | Yes | 2 | 1
Create class diagram (1) |  | Yes | 2 | 1
Create sequence diagram (1) |  | Yes | 2 | 1
Implement state pattern |  | Yes | 4 | 4